## Sheet1
Risk Register
Risk ID | Threat or Weakness | Risk Associated Assets | Possible Business Impact | Likelihood | Impact | Risk Score (Likelihood * Impact) | Risk Level | NIST CSF Mapping | Recommendation
R -01 | Microsoft 365 does not use MFA | Microsoft 365 emails | Attacker could read email, impersonate the employee, access shared files or send fraudulent payment requests | 4 | 5 | 20 | Critical | PR.AA | Enable MFA for all accounts
R -02 | Employees use shared accounts or reused password | Email, Accounting computer, Online Banking, Employees laptop | Unauthorized access to Critical Business data | 4 | 4 | 16 | Critical | PR.AA | Require individual accounts and stronger passwords
R -03 | Backups are inconsistent and untested | Accounting Computer, Inventory spreadsheet, Customer Records | Loss of business data | 3 | 5 | 15 | High | PR.IR, RC.RP | Schedule backups and test restoration
R -04 | Computers may not receive patches regularly | Accounting computer, Employees Laptop | Business Infrastructure may come to an hault, indirectly slowing down the production | 4 | 4 | 16 | Critical | PR.PS | Establish monthly patching procedures
R -05 | Employees recieves limited phishing training | Employees Laptop | Disclosure of business sensitive information to unauthorized individual | 4 | 4 | 16 | Critical | PR.AT | Conduct security-awareness training
R -06 | No documented incident response plan exists | Overall Company Assets | No proper plan and direction during the occurrence of unforeseen circumstances | 4 | 5 | 20 | Critical | RS.MA | Create a basic incident-response plan
R -07 | Personal USB devices may be used without controls | USB Drives, Employees Laptop | Ransomware Attacks or data corruption | 3 | 3 | 9 | Medium | PR.DS, PR.PS | Restrict and scan removable media
**Scoring metrics: 1–5: Low 6–10: Medium 11–15: High 16–25: Critical